## Sheet1
Tasks	Jul 15	Jul 22	Jul 29	Aug 05	Aug 12	Aug 19	Aug 26	Sep 02	Sep 09	Sep 16	Sep 23	Sep 30	Oct 07	Oct 14	Oct 21	Oct 28	Nov 04	Nov 11	Nov 18	Nov 25	Dec 02	Dec 09	Dec 16	Dec 23	Dec 30	Jan 06	Jan 13	Jan 20	Jan 27
Pre-internship setup
Familiarization with ROS2.0
+ Install ROS2.0 on Windows or Ubuntu
+ Import LD robot 3D model
+ Jog LD robot (teleop)

Visited ARTC to find out more about membership and training
- Membership rates for projects / - Participation in pre-competitive shared projects advancing ROS for industry-specific applications / - Full membership: Voting of priorities for shared projects / - Up to 3 free ROS trainings per year (2 for associate member) / - Up to 3 free seats for the Annual Workshop (2 for associate member) / - Full membership gets automatic associate tier access to the Europe and Americas regions as well – you could join their conference, send staff in these regions to their training, and participate in their pre-competitive projects / SGD7000/year for associate membership, pro-rated, 4k cash / Architecture advice is SGD125/hour: 8h*2days*10weeks = 160h = SGD20k

Engagement roadmap
ROS 1.0 training											x
Mentor intern when writing ROS layer											x	x
P&G pj using LD250 to move drums
CHART engagement?

Start of internship
Install Ubuntu ROS1.0 and Windows ROS 2.0 on T440 laptop
Introduce existing ROS packages with Omron robots for exploration
ROS-I Developer's Training 24-27/9 - Basic+Advanced SGD950each

ROS for LD robots
Understand how LD robot works (attach to Rajaram)
Learn ARCL commands
Choose ARCL functions to create ROS publishers
Able to write script to move LD robot a relative distance and to a pre-taught goal
Documentation and upload to GTKS (how can NSCs/customers use it)

ROS for TM robots (TM5-700)
Try TM ROS1.0 package available online
https://github.com/kentsai0319/techman_robot
Run Mobile Manipulator with ROS

ROS for Sysmac
Learn to write PLC programs on Sysmac Studio
Write FB to talk to ROS packages
Perform pick and place with Viper
Documentation and upload to GTKS (how can NSCs/customers use it)

Drone with LD robots
Try autonomous navigation of drone with ROS
Integrate LD navigation with drone action
Test in lab
Documentation and upload to GTKS (how can NSCs/customers use it)

ROS links
https://index.ros.org/doc/ros2/
https://index.ros.org/doc/ros2/Tutorials/
https://index.ros.org/doc/ros2/Installation/Dashing/
http://wiki.ros.org/navigation/Tutorials/RobotSetup
https://github.com/cse481wi18/cse481wi18/wiki/Lab-15%3A-Driving-with-odometry

## Plan - Matthew
			October			November					December					January					February
			29	30	31	1	4	5	6	7	8	11	12	13	14	15	18	19	20	21	22	25	26	27	28	29	2	3	4	5	6	9	10	11	12	13	16	17	18	19	20	23	24	25	26	27	30	31	1	2	3	6	7	8	9	10	13	14	15	16	17	20	21	22	23	24	27	28	29	30	31	3	4	5	6	7
	Task	Output	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F
	LD Robot
1	Draft out ROS diagram with nodes, topics for ARCL 'status' command	Diagram of package with nodes and topics / ROS package with correct structure and files
2	Create package with publishers for ARCL 'status' command	One node that publishes 5 topics - Status; BatteryVoltage; Location; LocalizationScore; Temperature
3	Split ARCL commands into topics, services or actions
4	Use namespaces to publish topics for multiple robots	Use lauch files
5	Write publishers for 5 ARCL commands	May need custom messages
6	Write publishers for remaining ARCL commands	May need custom messages
7	Write actions for 3 ARCL commands	e.g. patrol; dock
8	Write actions for remaining 7 ARCL commands
9	Write services for 10 ARCL commands	May need custom services
10	Write services for 20 ARCL commands	May need custom services
11	Write services for 20 ARCL commands	May need custom services
12	Write services for remaining ARCL commands	May need custom services
13	Functional tests of ROS packages on actual robot	Moving to goal; dock; patrol; say; move relative distance
14	Integration tests of ROS packages on actual robots	Move two robots between multiple goals
15	Document how to use code using inline comments and README	Instructions on how to install/modify code; limitations of code; what needs to be done on Mobile Planner
16	Get Rajaram to use ROS packages from Github	Goal: use documentations to write ROS code to move LD robot
17	Documentation

	TM Robot

	MoMa

## ARCL commands
	ARCL command [ARCL Reference Guide, 18448-000 Rev A, Updated: 1/19/2017]	Robot or EM	Grouping	Notes	TOPIC	SERVICE	ACTION
1	analogInputList Command 63	Robot	Hardware	Lists the named analog inputs
2	analogInputQueryRaw Command 64	Robot	Hardware	Queries the state of an analog input by raw
3	analogInputQueryVoltage Command 65	Robot	Hardware	Queries the voltage of an analog input
4	applicationFaultClear Command 66	Robot	Utilities	Clears a named application fault
5	applicationFaultQuery Command 67	Robot	Utilities	Gets the list of any application faults currently triggered
6	applicationFaultSet Command 69	Robot	Utilities	Sets an application fault
7	arclSendText Command 71	Both	Utilities	Sends the given message to all ARCL clients
8	configAdd Command 72	Both	Utilities	Enter sections and related configuration parameter keywords and values to the configuration list
9	configParse Command 74	Both	Utilities	Sends the configuration parameters to ARAM, which implements the configuration changes
10	configStart Command 76	Both	Hardware	Initialize a configuration list, similar to creating a task list. The configStart command overwrites any previous list.
11	connectOutgoing Command 78	Both	Hardware	Connects (or reconnects) a socket to the specified outside server
12	createInfo Command 79	Robot	Utilities	Creates a piece of information
13	dock Command 81	Robot	Motion	Sends the robot to the dock
14	doTask Command 82	Robot	Motion	Performs a single task.
15	doTaskInstant Command 84	Robot	Hardware	Performs an instant task - see list in Mobile Planner
16	echo Command 86	Both	Utilities	Enables/disables echo, or returns the current echo state
17	enableMotors Command 87	Robot	Hardware	Enables the robot motors, if the robot was not E-stopped
18	executeMacro Command 88	Robot	Utilities	Executes the specified macro
19	extIOAdd Command (shortcut: eda) 90	Both	Hardware	Creates a new external I/O set. This is a bank of inputs and outputs with a friendly name
20	extIODump Command (shortcut: edd) 92	Both	Hardware	Debug function used to dump the values of all the external I/Os. Only on if MP->Debug->DebugExternalIO is checked
21	extIODumpLocal Command (shortcut: eddl) 94	Robot	Hardware	Debug function used to dump the values of all the external I/Os. Only on if MP->Debug->DebugExternalIO is checked
22	extIOInputUpdate Command (shortcut: ediu) 96	Both	Hardware	Updates the values of the inputs for a specified external I/O set
23	extIOInputUpdateBit Command (shortcut: edib) 98	Both	Hardware	Updates a specific bit in the external digital input set.
24	extIOInputUpdateByte Command (shortcut: edi8) 100	Both	Hardware	Updates a specific byte in the named external digital output set
25	extIOOutputUpdate Command (shortcut: edou) 102	Both	Hardware	Updates the values of the outputs for an external I/O set. Meant to be used by the external device handling the real I/Os to update the output settings
26	extIOOutputUpdateBit Command (shortcut: edob) 104	Both	Hardware	/home/tthmatt/ld_ROS/src/om_aiv_util/scripts/ld_topic_publisher.py
27	extIOOutputUpdateByte Command (shortcut: edo8) 106	Both	Hardware	Updates a specific byte in the named external digital output device
28	extIORemove Command (shortcut: edr) 108	Both	Hardware	Removes an external I/O set
29	faultsGet Command 109	Robot	Utilities	Gets the list of any faults currently triggered
30	getConfigSectionInfo Command 111	Both	Hardware	Displays details about the configuration parameters in a specified section
31	getConfigSectionList Command 113	Both	Hardware	Displays the list of sections enabled in the ARAM configuration parameters
32	getConfigSectionValues Command 115	Both	Hardware	Displays the current parameter values for the specified section
33	getDataStoreFieldInfo Command (shortcut: dsfi) 117	Both	Utilities	Gets information on a field in the DataStore
34	getDataStoreFieldList Command (shortcut: dsfl) 119	Both	Utilities	Gets the list of field names in the DataStore
35	getDataStoreFieldValues Command (shortcut: dsfv) 121	Both	Utilities	Gets the values of a field in the DataStore
36	getDataStoreGroupInfo Command (shortcut: dsgi) 122	Both	Utilities	Gets the info on a group in the DataStore
37	getDataStoreGroupList Command (shortcut: dsgl) 124	Both	Utilities	Gets the list of groups in the DataStore
38	getDataStoreGroupValues Command (shortcut: dsgv) 125	Both	Utilities	Gets the values of a group in the DataStore
39	getDataStoreTripGroupList Command (shortcut: dstgl) 126	Both	Utilities	Returns the list of groups in the DataStore that contain trip information
40	getDateTime Command 127	EM	Utilities	Returns the system date and time
41	getGoals Command 128	Both	Utilities	Returns a list of goal names found in the current map
42	getInfo Command 129	Robot	Utilities	Returns the string associated with the information name
43	getInfoList Command 131	Robot	Utilities	Returns the list of information names
44	getMacros Command 133	Robot	Utilities	Displays a list of macros found in the current map
45	getRoutes Command 135	Robot	Utilities	Displays the list of route names found on the current map
	goTo Command
46	help Command 136	Both	Utilities	Provides a list and brief description of available ARCL commands.
47	inputList Command 137	Robot	Hardware	Lists the named digital inputs
48	inputQuery Command 139	Robot	Hardware	Queries the state of a named input
49	log Command 140	Both	Utilities	Logs the message to the normal log file
50	mapObjectInfo Command 142	Both	Utilities	Gets the information about a named map object
51	mapObjectList Command 144	Both	Utilities	Gets the names of map objects of a given type
52	mapObjectTypeInfo Command 146	Both	Utilities	Gets detailed information about a particular type of map object
53	mapObjectTypeList Command 148	Both	Utilities	Gets a list of the types of map objects in the map
54	newConfigParam Command 150	Both	Utilities	Adds a custom parameter to ARAM’s configuration, which can then be managed through ARCL or MobilePlanner
55	newConfigSectionComment Command 152	Both	Utilities	Adds a comment to a section
56	odometer Command 154	Robot	Hardware	Shows the robot trip odometer readings
57	odometerReset Command 155	Robot	Hardware	Resets the robot trip odometer
58	oneLineStatus Command 156	Robot	Utilities	Shows the status of the robot on one line of text
59	outputList Command 158	Robot	Hardware	Lists the named digital outputs
60	outputOff Command 160	Robot	Hardware	Turns off the named digital output
61	outputOn Command 161	Robot	Hardware	Turns on the named digital output
62	outputQuery Command 162	Robot	Hardware	Queries the state of a named output
63	patrol Command 164	Robot	Motion	Initiates continuous patrol of the named route
64	patrolOnce Command 166	Robot	Motion	Patrol the named route one time
65	patrolResume Command 168	Robot	Motion	Continue navigating the current route.
66	payloadQuery Command (shortcut: pq) 170	EM	Hardware	Queries the payload for a specified robot, a specified robot and slot, or all connected robots that have a payload configured
67	payloadQueryLocal Command (shortcut: pql) 173	Robot	Hardware	Queries the payload for the robot and specified slot
68	payloadRemove Command (shortcut: pr) 175	Robot	Hardware	Empties the specified payload slot on the robot
69	payloadSet Command (shortcut: ps) 177	Robot	Hardware	Defines a payload slot on this robot
70	payloadSlotCount Command (shortcut: psc) 179	EM	Hardware	Displays the slot count on a specific robot or on all robots
71	payloadSlotCountLocal Command (shortcut: pscl) 181	Robot	Hardware	Displays a slot count on this robot
72	play Command 182	Robot	Hardware	Plays a .wav sound file on the robot
73	popupSimple Command 184	Both	Utilities	Display a popup message in the MobilePlanner software
74	queryDockStatus Command 186	Robot	Hardware	Gets the docking/charging status
75	queryFaults Command (shortcut: qf) 187	EM	Hardware	Displays the faults associated with the specified robot
76	queryMotors Command 190	Robot	Hardware	Gets the state of the robot motors
77	queueCancel Command (shortcut: qc) 192	EM	Motion	Cancels a queued request for a robot by type or value
78	queueCancelLocal Command (shortcut: qcl) 195	Robot	Motion	Cancels a queued request for a robot by type or value
79	queueDropoff Command (shortcut: qd) 198	Robot	Motion	Queues the robot to the dropoff goal
80	queueModify Command (shortcut: qmod) 201	EM	Motion	Allows modification of goal and priority for job segments
81	queueModifyLocal Command (shortcut: qmodl) 207	Robot	Motion	Allows modification of goal and priority for job segments
82	queueMulti Command (shortcut: qm) 212	EM	Motion	Queues the robot for multiple pickups and dropoffs at multiple goals
83	queuePickup Command (shortcut: qp) 216	EM	Motion	Calls any available robot for a pick up request
84	queuePickupDropoff Command (shortcut: qpd) 219	EM	Motion	Queues a pick-up and drop-off request for any available robot.
85	queueQuery Command (shortcut: qq) 224	EM	Motion	Shows the job status of the queue by type or value
86	queueQueryLocal Command (shortcut: qql) 227	Robot	Motion	Shows the job status of the robot queue by type or value
87	queueShow Command (shortcut: qs) 230	EM	Motion	Shows the status of the last 11 jobs in the queue, including any jobs assigned to the robots and the status of each job
88	queueShowCompleted Command (shortcut: qsc) 232	EM	Motion	Shows the jobs in the queue with a status of Completed
89	queueShowRobot Command (shortcut: qsr) 234	EM	Hardware	Shows the status and substatus of all robots (or, optionally, a specific robot) connected to the Enterprise Manager
90	queueShowRobotLocal Command (shortcut: qsrl) 236	Robot	Hardware	displays the status of the robot
91	quit Command 237	Both	Utilities	Closes the connection to the server.
92	say Command 238	Robot	Utilities	Speak a text string through the robot audio output
93	shutdown Command 239	Robot	Utilities	Shuts down the robot
94	status Command 240	Robot	Utilities	Returns the operational state of the robot
95	stop Command 242	Robot	Motion	Stops the current robot motion
96	tripReset Command (shortcut: tr) 243	Both	Utilities	Resets the trip values in the DataStore.
97	undock Command 245	Robot	Motion	Undocks the robot
98	updateInfo Command 246	Robot	Utilities	Updates the value for an existing piece of information.
99	waitTaskCancel Command 248	Robot	Utilities	Cancels a wait task if one is active
100	waitTaskState Command 250	Robot	Utilities	Displays the status of the wait task
					#NAME?	#NAME?	#NAME?
	addCustomCommand			Adds a custom command that'll send a message out ARCL when called
	addCustomStringCommand			Adds a custom string command that'll send a message out ARCL when called
	applicationBlockDrivingClear			Clears an application blockDriving [abdc]
	applicationBlockDrivingSet			Sets an application blockDriving [abds]
	centralServer			Gets information about the central server connection
	executeMacroTemplate			executes a specified macro template with the given parameters
	freeMotors			Frees the motors (note that the brakes are not enabled, so this is / Unsafe and should only be used by trained personnel in careful conditions)
	getMacroTemplates			gets a list of macro templates in the map / (for use with executeMacroTemplates)
	getPoseEncoder			Gets the encoder pose of the robot
	go			Stops the robot from any wait it is doing then resume patrolling or makes / The robot idle 2 minutes so that it will resume doing queued jobs / (with the right parameters). See also stay.
	goalDistanceRemaining			Gets the distance remaining to robots goals
	goalDistanceRemainingLocal			Gets the distance remaining to this robot's goal
	Localizes to a given goal [lag]			localizeAtGoal
	MARCOverrideAnalog			Usage: <command> <0-15> <flags as int or hex (16 bits)> / This overrides the normal analog from MARC for purposes of testing. / Hex will work. [moa]
	MARCOverrideAnalogOut			Usage: <command> <0-3> <flags as int or hex (16 bits)> / This overrides the normal analog output from MARC for purposes of testing. / Hex will work. [moo]
	MARCOverridePowerStatus1			Usage: <command> <flags as int or hex (8 bits)> / This overrides the normal flags from MARC for purposes of testing. / Hex will work. [mops1]
	MARCOverridePowerStatus2			Usage: <command> <flags as int or hex (8 bits)> / This overrides the normal flags from MARC for purposes of testing. / Hex will work. [mops2]
	modeLock			Locks the current mode
	modeQuery			Queries the current mode and it's lock status
	modeUnlock			Unlocks the current mode
	newConfigParamEnd			Finishes adding multiple params to the config. Must be paired with a / NewConfigParamStart.
	newConfigParamStart			Starts adding multiple params to the config. Optional. If specified, / Must be followed by a newConfigParamEnd.
	newConfigSectionComment			Adds a comment to a section (shows up in MP)
	queueCancelMultiSegment			Cancels a multi goal job segment by id [qcms]
	waitTaskFail			Fails the wait task (if it's active)
	waitTaskState			Gets the state of the wait task

## test
Test Objective	Precondition	Steps	Test data	Expected results	Post-condition
Move robot to mulitple / Goals with ros	Goals have to be set / In mobile planner	Roslauch om_aiv_navigation robot1.py / rosrun om_aiv_navigation test.py		robot moves to goal 1 / Then goal 4
Get status of 2 robots / At the same time	robots ips have to be / Set in the launch file				the launch files runs the services server with / different names as set in the service client file / Rospy.wait forservice due to launching 2 of the / Same service servers for robot1 and robot2 each. / So the client file keep waiting for the service with / The specific name but the service which run is of / A different name.
Test topic applicationFaultQuery / On actual robot.	robot ip have to be / Set when launching launch / File as command line arg	1. Open 3 terminal windows / 2. In one terminal run command: “roscore” / 3. In second terminal window, run command: roslaunch om_aiv_util test_roslaunch.launch ip:=168.3.201.122 (ip address is unique to each robot) / 4. In third terminal windows, run command: rostopic echo /ldarcl_ApplicationFaultQuery to suscribe to topic / 5. Ctrl C in third terminal to stop suscribing to topic. repeat step 4 and suscribe to required topic. A list of topics can be viewed using rostopic list.		In third terminal windows, you should see data: "ApplicationFaultQuery: <fault status> where the <fault status> is the fault.	In third terminal window data recieved is : data: "ApplicationFaultQuery: No Faults"
Test topic faultsGet / On actual robot.				In third terminal windows, you should see data: "FaultsGet: <fault status>" / where the <fault status> is the fault.	data: "FaultsGet: No faults"
Test topic getDateTime / On actual robot.				In third terminal windows, you should see data: data: "<date and time> / where the <date and time> is the date and time	data: "DateTime: 12/03/2019 05:03:04"
Test topic odometer / On actual robot.				In third terminal windows, you should see data: "<odometer> / where <odometer> odometer values	data: "Odometer: 280 mm 369 deg 68978 sec"
Test topic oneLineStatus / On actual robot.				In third terminal windows, you should see data: "<oneLineStatus> / where <oneLineStatus> is the status of the robot on one line of text	data: "Status: DockingState: Docked ForcedState: Unforced ChargeState: Float StateOfCharge:\ / \ 98.5 Location: 640 27815 180 Temperature: 36"
Test topic queryDockStatus / On actual robot.				In third terminal windows, you should see data: "<dockStatus> / where <dockStatus> is the docking/charging status	data: "DockingState: Docked ForcedState: Unforced ChargeState: Float"
Test topic queryMotors / On actual robot.				In third terminal windows, you should see data: "<MotorStatus> / where <MotorStatus> is state of the motors	data: "EStop relieved but motors still disabled"
Test topic queueShowRobotLocal / On actual robot.				In third terminal windows, you should see data: "<status> / where <status> is status of the robot	data: "QueueRobot: \"Robot122\" UnAvailable Interrupted \"\""
Test topic waitTaskState / On actual robot.				In third terminal windows, you should see data: "<waitTaskState> / where <waitTaskState> is the status of the wait task	data: "WaitState: Not waiting"
Test 20 getInfo topics / On actual robot.				In third terminal windows, you should see data: "<info> / where <info> is the string associated with the information name	for example rostopic echo /ldarcl_getInfo_Idle: / data: 67572
Test 6 status topics On actual robot.				In third terminal windows, you should see data: "<status> / where <status> is the operational state of the robot	for example rostopic echo /ldarcl_status_temperature: / data: 36.0

Test analogInputList service on actual robot.	robot ip have to be / Set when launching launch / File as command line arg	1. Open 3 terminal windows / 2. In one terminal run command: “roscore” / 3. In second terminal window, run command: roslaunch om_aiv_util test_roslaunch.launch ip:=168.3.201.122 (ip address is unique to each robot) / 4. In third terminal windows, run command: rosrun om_aiv_util analogInputList_client.py / 5. repeat step 4 for other services and input command line arguments if required		In third terminal window, you should see the named analog inputs	running command / ['AnalogInputListHelper: List format is: <minVoltage> <maxVoltage> <maxRaw> <name>', 'AnalogInputListHelper: The data returned by analogInputQueryVoltage is a voltage as a double between <minVoltage> and <maxVoltage>', 'AnalogInputListHelper: The data returned by analogInputQueryRaw is an int called <rawValue>', "AnalogInputListHelper: To get <rawValue> to voltage do '<minVoltage> + (<maxVoltage> - <minVoltage>) * <rawValue> / <maxRaw>", 'End of AnalogInputList']
Test analogInputQueryRaw service on actual robot.				In third terminal window, the state of an analog input by raw is shown	['name'] / running command / CommandError: analogInputQueryRaw name / CommandErrorDescription: Must give device to query
Test analogInputQueryRaw service on actual robot.
Able specify robot name and / Ip address as command line args / When runing launch file				Able to specify robot / name and / Ip address as / Command line args / When runing launch file

testplan
Actions – queuepickup drop off
firmware version	ARAM 4.9.27	ARAM 5.0.12
have another file to pass arguments to launch file from txt file
timeout for rospy.waitforservice
Readme – arcl doumentation
another package to have user client programs to call server programs

1. Dont need so many servers
2. Dynamic service srv file – just one
3. ld_status_publisher init node once can already
4. rate.sleep – remove from files – use rosTime – ld publisher
5. use rospy.spin dont need loop forever – ld publisher
6. make package compatible with future/newer ros versions

## getInfo
InfoList: WirelessLink
InfoList: WirelessQuality
InfoList: Odometer(KM)
InfoList: HourMeter
InfoList: Temperature(C)
InfoList: LaserScore
InfoList: LaserLock
InfoList: LaserNumSamples
InfoList: LaserNumPeaks
InfoList: MPacs
InfoList: Laser_1 Pacs
InfoList: SBC Uptime
InfoList: ARAM Uptime
InfoList: Idle
InfoList: TipAngle
InfoList: IsTipped
InfoList: Queue ID
InfoList: Queue Job ID
InfoList: DebugLogState
InfoList: DebugLogSeconds

## block diagram
ROS Launch File for Actions
om_aiv_package
om_aiv_navigation
package
ROS Launch File for
Services and Topics

LD_ROS
workspace

Action servers
(waiting for
client/s)

Action client/s
(send command
to client)

waiting
Action server file/s
sends command
 To ARCL
Topics published

Service servers
(waiting for client)

Rostopic echo
Subscribes to
topic/s

Service client/s
(send command
to client)
waiting
Service server file/s
sends command
 To ARCL

Get back response
And required data

Robot executes
command/s.
Get back response/s

## Sheet6
convert queuedrop off to action
Action client can be implemented in user program
test plan and doumentation